IMPLEMENTATION HANDBOOK

India → US Local SMB Services
Study Guide & Next-Phase Execution Playbook

From Analysis → Action: A Working Document for
Study, Decision-Making & Implementation

| Document Type | Implementation Handbook & Study Guide |
| --- | --- |
| Companion Files | Handover Document (.docx) + Analysis Spreadsheet (.xlsx) |
| Date | July 14, 2026 |
| Intended Audience | Founders, Ops Leads, Delivery Managers, Sales Leads |
| Purpose | Study the analysis → Make decisions → Execute Phase 1 |

# How to Use This Document

This is NOT a read-once-and-file document. It's a working handbook designed to be used over 4-6 weeks as your team studies the market analysis and builds toward launch. It contains:

| Section | Purpose | When to Use |
| --- | --- | --- |
| Part A: Study Guide | Structured reading plan for the analysis data | Week 1 — Read before any decisions |
| Part B: Decision Worksheets | Fill-in worksheets for vertical & service selection | Week 1-2 — Fill out as a team |
| Part C: Implementation Playbook | Step-by-step build plan for Phase 1 | Week 2-6 — Execute sequentially |
| Part D: Delivery Blueprint | How to actually deliver the services | Week 3-6 — Build alongside sales |
| Part E: Sales & Client Acquisition | How to find and close first clients | Week 4-8 — Start early, iterate |
| Part F: Operations & Tools | Tech stack, team structure, SOPs | Week 2-4 — Set up early |
| Part G: KPIs & Tracking | What to measure and how | Week 4+ — Track from day 1 |
| Part H: 12-Week Sprint Calendar | Day-by-day execution timeline | Throughout — Reference weekly |

📋 Recommended approach: Assign Part A as reading for Week 1. Hold a team workshop at end of Week 1 to complete Part B worksheets. Then begin Part C execution in Week 2.

# PART A: STUDY GUIDE

Purpose: Structured reading plan to deeply understand the 161-service analysis before making any decisions.

## A1. Day 1-2: Understand the Scoring Framework

Before looking at specific services, understand HOW they were scored.

### Reading Assignments:

Spreadsheet → Sheet 'Legend & Notes' — Read every parameter definition

Spreadsheet → Sheet 'Summary Dashboard' — Understand tier distribution

Handover Doc → Section 3 (Scope & Methodology) — How the Opportunity Score works

Handover Doc → Section 4 (Tier Framework) — What each tier means strategically

### Study Questions (answer after reading):

☐  What are the 5 scoring parameters and what does each measure?

☐  What is the scoring formula? (Automation % + Competition Modifier + Confidence Modifier)

☐  Why does competition have a bigger modifier (−25) than confidence (+10)?

☐  What score range maps to each tier? (Platinum ≥85, Gold 70-84, Silver 52-69, Bronze 38-51, Red <38)

☐  Why did we use a 0-120 scale instead of 0-100?

☐  What's the difference between 'Automation Potential' and 'Automation Confidence'?

💡 Key Insight: Competition matters MORE than automation confidence. A service that's 90% automatable in a Very High competition market scores LOWER than a 70% automatable service in a Low competition market. This is deliberate — market positioning beats technical capability.

────────────────────────────────────────────────────────────────────────────────

## A2. Day 3: Study the Platinum Tier (63 Services)

These are your immediate-launch opportunities. Understand them deeply.

### Reading Assignments:

Spreadsheet → Filter by Tier = 'Platinum' (column I)

Sort by Score (column J) descending — study the top 20

Handover Doc → Section 6.1 (Platinum Tier Analysis)

Handover Doc → Section 5.2 (The Sweet Spot)

### Study Questions:

☐  Which 5 Platinum services have the highest scores? What do they have in common?

☐  What are the top 3 Platinum clusters? (Scheduling/Routing, Compliance, Customer Communication)

☐  Which verticals have the MOST Platinum services? List them.

☐  For each Platinum service, read the 'CAN' vs 'CANNOT' column. What tasks still need humans?

☐  What's the average ticket size for Platinum services? (Compare to Bronze/Red Flag)

☐  Which Platinum services use SaaS delivery vs. retainer vs. per-task? What does this mean for operations?

🔍 Pattern Recognition: Almost all Platinum services are 'boring back-office' work — scheduling, compliance, billing, reminders. The unsexy stuff that SMBs hate doing. This is your opportunity. Glamorous services (social media, branding, lead gen) score poorly.

────────────────────────────────────────────────────────────────────────────────

## A3. Day 4: Study the Gold Tier (46 Services) + Verticals

Gold tier services are strong but need more strategy. Understand the difference.

### Reading Assignments:

Spreadsheet → Filter by Tier = 'Gold' — Study all 46

Handover Doc → Section 6.2 (Gold Tier Analysis)

Handover Doc → Section 7 (Top 10 Verticals)

Handover Doc → Section 8 (Automation vs Competition Matrix)

### Study Questions:

☐  What's the #1 reason a Gold service isn't Platinum? (Usually: higher competition)

☐  Which Gold services could become Platinum with niche positioning? Give 3 examples.

☐  For each top-10 vertical, list the Platinum + Gold services available

☐  Which vertical has the highest TOTAL opportunity (Platinum + Gold combined)?

☐  In the Automation vs Competition matrix, where do most services cluster?

☐  What's the 'Sweet Spot' quadrant and how many services are in it?

────────────────────────────────────────────────────────────────────────────────

## A4. Day 5: Study the Risk Assessment + GTM Strategy

### Reading Assignments:

Handover Doc → Section 9 (Risk Assessment) — All 7 risks

Handover Doc → Section 10 (Go-to-Market Recommendations) — 4 strategic plays

Handover Doc → Section 11 (90-Day Plan)

Handover Doc → Section 12 (Open Questions) — These are YOUR decisions to make

### Study Questions:

☐  Which risk has the highest severity + highest likelihood? (AI Displacement)

☐  What are the 4 strategic plays? Which one fits your team's strengths?

☐  What does the 90-day plan look like in summary? (Discovery → Build → Pilot → Launch)

☐  List the 10 open questions. Which 3 are most critical to answer first?

☐  What's the recommended pricing philosophy? (40-60% of US rates, not 80% discount)

☐  What's the recommended sales channel for fastest revenue? (White-label partnerships)

────────────────────────────────────────────────────────────────────────────────

## A5. Day 5: Deep-Dive Your Shortlisted Verticals

By now you should have 2-3 verticals in mind. Spend Day 5 going DEEP on each one.

### For Each Shortlisted Vertical, Research:

☐  How many SMBs exist in this vertical in the US? (Google: '[vertical] businesses in US statistics')

☐  What's the average revenue of an SMB in this vertical?

☐  What software/tools do they currently use? (Check G2, Capterra reviews in this category)

☐  What are the top 3 pain points mentioned in online forums/reviews? (Reddit, Facebook groups)

☐  Who are the existing India-based service providers for this vertical? (Clutch, Upwork search)

☐  What's the regulatory/compliance environment? (HIPAA? FCRA? State licensing?)

☐  What's the seasonality pattern? (When are they busiest? When do they buy services?)

☐  What would a 'dream client' look like in this vertical? (Size, location, revenue, tech adoption)

🎯 Pro Tip: Join 2-3 Facebook groups or Reddit communities for your shortlisted verticals. lurk for a week. The complaints and questions you see = your service opportunities.

# PART B: DECISION WORKSHEETS

Purpose: Structured worksheets to make key decisions as a team. Complete these by end of Week 2.

## B1. Vertical Selection Worksheet

Score each candidate vertical on these criteria. Total the scores to rank them.

| Criteria | Weight | Vertical 1: ___ | Vertical 2: ___ | Vertical 3: ___ |
| --- | --- | --- | --- | --- |
| # of Platinum services available | ×3 | __ /10 → __ | __ /10 → __ | __ /10 → __ |
| Market size (# of SMBs in US) | ×3 | __ /10 → __ | __ /10 → __ | __ /10 → __ |
| Average ticket size potential | ×2 | __ /10 → __ | __ /10 → __ | __ /10 → __ |
| Team's existing domain knowledge | ×2 | __ /10 → __ | __ /10 → __ | __ /10 → __ |
| Low competition from India providers | ×2 | __ /10 → __ | __ /10 → __ | __ /10 → __ |
| Recurring revenue potential | ×2 | __ /10 → __ | __ /10 → __ | __ /10 → __ |
| Ease of client acquisition | ×1 | __ /10 → __ | __ /10 → __ | __ /10 → __ |
| Regulatory barrier (lower = better) | ×1 | __ /10 → __ | __ /10 → __ | __ /10 → __ |
|  | TOTAL | ___ | ___ | ___ |

Decision: Primary vertical = _______________  |  Secondary vertical = _______________

## B2. Service Selection Worksheet

For your chosen primary vertical, select 3-5 services to launch with.

| Service Name | Tier | Score | Ticket Size | Why This Service? | Delivery Complexity |
| --- | --- | --- | --- | --- | --- |
| 1. _______________ | ____ | ___ | $___/mo |  | □ Low □ Med □ High |
| 2. _______________ | ____ | ___ | $___/mo |  | □ Low □ Med □ High |
| 3. _______________ | ____ | ___ | $___/mo |  | □ Low □ Med □ High |
| 4. _______________ | ____ | ___ | $___/mo |  | □ Low □ Med □ High |
| 5. _______________ | ____ | ___ | $___/mo |  | □ Low □ Med □ High |

💡 Selection Rule: Pick at least 1 'anchor' service (highest score, easiest to deliver) and 1 'differentiator' service (unique, competitors don't offer it). The anchor gets clients in the door; the differentiator keeps them.

## B3. Service Package Design Worksheet

Design your 3-tier offering for each vertical.

|  | Starter | Growth | Enterprise |
| --- | --- | --- | --- |
| Package Name |  |  |  |
| Services Included |  |  |  |
| Monthly Price (USD) | $___ – $___ | $___ – $___ | $___ – $___ |
| Setup Fee | $___ | $___ | $___ |
| Target Client Profile | Solo / 1 location | 2-5 locations | 5+ locations / franchise |
| Key Deliverables |  |  |  |
| SLA / Response Time |  |  |  |
| Estimated Delivery Cost | $___/client/mo | $___/client/mo | $___/client/mo |
| Target Gross Margin | ___% | ___% | ___% |

## B4. Team Requirements Worksheet

| Role | # Needed | Skills Required | Hire/Train/Outsource | Monthly Cost |
| --- | --- | --- | --- | --- |
| Vertical Domain Lead | ___ |  | □ Hire □ Train □ Outsource | $___ |
| Delivery Specialist(s) | ___ |  | □ Hire □ Train □ Outsource | $___ |
| Sales / BD (US-facing) | ___ |  | □ Hire □ Train □ Outsource | $___ |
| Tech / Automation Engineer | ___ |  | □ Hire □ Train □ Outsource | $___ |
| QA / Client Success | ___ |  | □ Hire □ Train □ Outsource | $___ |
| Project Manager | ___ |  | □ Hire □ Train □ Outsource | $___ |
|  | TOTAL |  |  | $___/mo |

## B5. Competitive Positioning Worksheet

For each service, map the competitive landscape and define your angle.

| Service | US Competitors (who offers this?) | India Competitors (Clutch/Upwork) | Their Price Range | Your Differentiator |
| --- | --- | --- | --- | --- |
| ________ |  |  | $___ – $___ |  |
| ________ |  |  | $___ – $___ |  |
| ________ |  |  | $___ – $___ |  |

🎯 Positioning Framework: 'We help [VERTICAL] businesses in [GEOGRAPHY] achieve [OUTCOME] by [UNIQUE MECHANISM], unlike [COMPETITOR] who [THEIR WEAKNESS].'

# PART C: IMPLEMENTATION PLAYBOOK

Purpose: Step-by-step execution plan for Phase 1. Each step has owners, deliverables, and deadlines.

## C1. Week 1: Foundation & Decisions

| Day | Task | Owner | Deliverable | Done? |
| --- | --- | --- | --- | --- |
| Mon | Team reads Part A of this handbook (Day 1-2 assignments) | All | Everyone completes study questions | ☐ |
| Tue | Team reads Part A (Day 3-5 assignments) | All | Study questions answered | ☐ |
| Wed | Deep-dive research on 3 shortlisted verticals (A5) | BD Lead | Vertical research briefs | ☐ |
| Thu | Team workshop: Complete B1 (Vertical Selection) worksheet | All | Primary + Secondary vertical selected | ☐ |
| Thu | Complete B2 (Service Selection) worksheet | All | 3-5 launch services selected | ☐ |
| Fri | Complete B3 (Package Design) worksheet | Ops Lead | 3-tier pricing defined | ☐ |
| Fri | Complete B4 (Team Requirements) worksheet | Ops Lead | Hiring plan drafted | ☐ |
| Fri | Complete B5 (Competitive Positioning) worksheet | BD Lead | Positioning statements written | ☐ |

## C2. Week 2: Build Service Delivery

| Day | Task | Owner | Deliverable | Done? |
| --- | --- | --- | --- | --- |
| Mon | Set up delivery tools & accounts (see Part F) | Tech Lead | All tools provisioned | ☐ |
| Mon | Build automation workflows for Service #1 | Tech Lead | Workflow documented & tested | ☐ |
| Tue | Build automation workflows for Service #2 | Tech Lead | Workflow documented & tested | ☐ |
| Tue | Write Delivery SOP for Service #1 (see Part D template) | Ops Lead | SOP document v1 | ☐ |
| Wed | Write Delivery SOP for Service #2 | Ops Lead | SOP document v1 | ☐ |
| Wed | Create client onboarding template & process | Ops Lead | Onboarding checklist + welcome email | ☐ |
| Thu | Internal training: team delivers mock service for pilot client | Domain Lead | Training completed | ☐ |
| Thu | Create sales materials: one-pager, pricing sheet, capabilities deck | BD Lead | Sales kit v1 | ☐ |
| Fri | Identify & reach out to 10 potential pilot clients | BD Lead | Outreach sent, 10 prospects contacted | ☐ |
| Fri | Build CRM/pipeline for tracking prospects | BD Lead | CRM set up with 10 leads | ☐ |

## C3. Weeks 3-4: Pilot Delivery

| Week | Task | Owner | Deliverable | Done? |
| --- | --- | --- | --- | --- |
| 3 | Close 3-5 pilot clients (free or 80% discount for case study rights) | BD Lead | 3-5 signed pilot agreements | ☐ |
| 3 | Onboard pilot clients: collect access, data, preferences | Ops Lead | All pilots onboarded | ☐ |
| 3 | Begin delivering Service #1 to pilots | Delivery Team | First deliverables sent | ☐ |
| 3 | Daily standup: what's working, what's broken | Ops Lead | Issues log updated daily | ☐ |
| 4 | Continue delivery + begin Service #2 for pilots | Delivery Team | Both services active | ☐ |
| 4 | Collect metrics: time spent, client satisfaction, results achieved | Ops Lead | Metrics dashboard v1 | ☐ |
| 4 | Collect testimonials + before/after data from pilots | BD Lead | 2-3 testimonials drafted | ☐ |
| 4 | Refine SOPs based on pilot learnings | Ops Lead | SOPs v2 (updated) | ☐ |
| 4 | Convert pilots to paid (or extend with case study agreement) | BD Lead | Pilot → Paid conversion plan | ☐ |

## C4. Weeks 5-8: Launch & Scale

| Week | Task | Owner | Deliverable | Done? |
| --- | --- | --- | --- | --- |
| 5 | Publish 2-3 case studies from pilots | Marketing | Published case studies | ☐ |
| 5 | Begin outbound sales campaign (email + LinkedIn) | BD Lead | 50 prospects contacted | ☐ |
| 5 | Launch white-label partnership outreach (5 US agencies) | BD Lead | 5 partnership proposals sent | ☐ |
| 6 | Continue outbound + follow up on partnerships | BD Team | Pipeline: 20+ active prospects | ☐ |
| 6 | Build remaining services (Service #3, #4, #5) | Tech Lead | All services operational | ☐ |
| 6 | Attend 1 industry event / join 2 online communities | BD Lead | Network connections made | ☐ |
| 7 | Close first 5-10 paying clients | BD Team | 5-10 signed contracts | ☐ |
| 7 | Onboard paying clients using refined process | Ops Lead | All new clients onboarded | ☐ |
| 7 | Review KPIs: CAC, margin, NPS, delivery quality | Ops Lead | KPI report #1 | ☐ |
| 8 | Team retrospective: what worked, what didn't | All | Retrospective doc | ☐ |
| 8 | Plan Phase 2: additional services, second vertical | Leadership | Phase 2 brief | ☐ |

# PART D: DELIVERY BLUEPRINT

Purpose: Templates and frameworks for actually delivering services to clients.

## D1. Service Delivery SOP Template

Copy this template for each service you deliver. Fill in the blanks.

| Field | Value |
| --- | --- |
| Service Name |  |
| Service Tier | □ Starter □ Growth □ Enterprise |
| Vertical |  |
| Client's Weekly Time Commitment | ___ minutes/week |
| Our Weekly Time Commitment | ___ hours/week |
| DELIVERY PROCESS |  |
| Step 1: Client Onboarding |  |
| Tools to set up |  |
| Access/credentials needed |  |
| Information to collect |  |
| Timeline |  |
| Step 2: Weekly/Monthly Delivery |  |
| What we deliver |  |
| What's automated vs. manual |  |
| Quality checkpoints |  |
| Client approval needed? |  |
| Step 3: Reporting & Communication |  |
| What reports we send |  |
| Frequency |  |
| Communication channels |  |
| Step 4: Escalation & Issue Handling |  |
| Common issues & resolution |  |
| Escalation path |  |
| SLA commitments |  |
| AUTOMATION MAP |  |
| Task 1: ____ → □ Fully Auto □ Semi-Auto □ Manual |  |
| Task 2: ____ → □ Fully Auto □ Semi-Auto □ Manual |  |
| Task 3: ____ → □ Fully Auto □ Semi-Auto □ Manual |  |
| Task 4: ____ → □ Fully Auto □ Semi-Auto □ Manual |  |
| Task 5: ____ → □ Fully Auto □ Semi-Auto □ Manual |  |
| QUALITY METRICS |  |
| Accuracy target | ___% |
| Turnaround time target | ___ hours/days |
| Client satisfaction target | ___/10 NPS |

────────────────────────────────────────────────────────────────────────────────

## D2. Client Onboarding Checklist

Standard onboarding process for every new client.

Pre-Onboarding (Before Kickoff Call)

☐  Signed contract / MSA received

☐  Setup fee invoice sent and paid

☐  Welcome email sent with onboarding questionnaire

☐  Internal kickoff brief prepared (client info, goals, contacts)

☐  Delivery team assigned and briefed

☐  Tool accounts created (if client needs access to our platforms)

Kickoff Call (30-60 min)

☐  Introductions: our team + their team

☐  Review scope of services (what's included, what's not)

☐  Collect access: logins, data exports, brand assets, etc.

☐  Set expectations: timelines, communication cadence, reporting

☐  Define success metrics: what does 'winning' look like?

☐  Schedule recurring check-in calls (weekly/biweekly)

☐  Identify their preferred communication channel (email/Slack/WhatsApp)

Setup Phase (Week 1)

☐  All access credentials received and tested

☐  Audit/assessment completed (current state analysis)

☐  Automation workflows configured and tested

☐  First deliverable sent for client review

☐  Feedback collected and incorporated

☐  Client confirmed: 'This looks right, proceed with regular delivery'

Steady State (Week 2+)

☐  Regular delivery cadence established

☐  First monthly report sent

☐  First check-in call completed

☐  NPS / satisfaction survey sent (after 30 days)

☐  Upsell/cross-sell opportunity identified (if applicable)

────────────────────────────────────────────────────────────────────────────────

## D3. Automation Stack by Service Category

Recommended tools and platforms for automating each service category.

| Service Category | Primary Automation Tools | Backup / Alternatives | Monthly Cost |
| --- | --- | --- | --- |
| Scheduling & Routing | Route4Me, Google Maps API, Calendly | OptimoRoute, Workiz, Jobber | $50-$200/mo |
| Customer Communication | GoHighLevel (GHL), Twilio, Mailchimp | ActiveCampaign, Klaviyo, SimplePractice | $100-$400/mo |
| Compliance & Documentation | Airtable, Notion, Google Workspace | Monday.com, Smartsheet, DocuWare | $50-$200/mo |
| Billing & Accounting | QuickBooks Online, Stripe, Bill.com | Xero, FreshBooks, Wave | $50-$150/mo |
| CRM & Pipeline | GoHighLevel, HubSpot, Zoho CRM | Pipedrive, Salesforce (for enterprise) | $100-$500/mo |
| AI & Content | ChatGPT/Claude API, Canva, CapCut | Jasper, Copy.ai, Descript, Midjourney | $50-$300/mo |
| Document Processing | Zapier, Make.com, Google Apps Script | n8n, Power Automate, custom Python | $20-$200/mo |
| Reporting & Dashboards | Google Looker Studio, Airtable | Tableau, Power BI, custom dashboards | $0-$100/mo |

💰 Cost-Saving Tip: GoHighLevel ($97-$297/mo) covers CRM + email + SMS + booking + landing pages + reviews + pipelines in ONE platform. For most verticals, this single tool replaces 4-5 separate subscriptions.

# PART E: SALES & CLIENT ACQUISITION PLAYBOOK

Purpose: How to find and close your first 10 clients.

## E1. Acquisition Channel Strategy

| Channel | Effort | Cost | Speed to Revenue | Best For | How to Execute |
| --- | --- | --- | --- | --- | --- |
| White-Label Partnerships | Medium | Low | Fast (2-4 wks) | Quickest path. Partner with US marketing agencies, business consultants, or industry SaaS companies who need delivery partners. | Identify 20 agencies serving your vertical. Send personalized pitch. Offer free pilot project. |
| Cold Email Outreach | High | Low | Medium (4-8 wks) | Direct to SMB owners. Works best for verticals where you can clearly articulate pain + solution in 3 sentences. | Build list of 500 prospects. 3-email sequence. Follow up by phone. Offer free audit/assessment. |
| LinkedIn Outreach | Medium | Low | Medium (4-8 wks) | Best for B2B verticals (property management, construction, accounting). Decision-makers are active on LinkedIn. | Optimize profile. Connect with 50/week. Share valuable content. DM after connection with specific insight. |
| Industry Events / Trade Shows | High | High | Slow (8-12 wks) | Best for high-ticket services. Face-to-face trust building. Ideal for construction, legal, healthcare verticals. | Attend 1-2 events per quarter. Pre-schedule 10 meetings. Follow up within 48 hours. |
| Referral Program | Low | Low | Medium (4-8 wks) | After first 5 clients. Ask for referrals. Offer $200-$500 referral fee or 1 month free. | Formal referral program. Ask after NPS score of 8+. Make it easy (warm intro > cold referral). |
| Content Marketing / SEO | High | Low | Slow (3-6 mo) | Long-term play. Write for your vertical's publications. Guest posts. YouTube tutorials. Build authority. | Publish 2 articles/week. Target long-tail keywords for your vertical. Guest post on industry blogs. |

────────────────────────────────────────────────────────────────────────────────

## E2. Cold Email Templates

### Template 1: Pain-Agitation-Solution

Subject: [Specific pain point they likely have]

Hi [First Name],

I noticed [specific observation about their business — e.g., 'your Google listing shows 47 reviews but your competitor has 200+']. Most [vertical] businesses in [area] struggle with [pain point].

We help [vertical] businesses [achieve outcome] by [unique mechanism]. [Social proof: 'Recently helped a [similar business] achieve [specific result] in [timeframe].']

Would it make sense to have a quick 15-min call this week to see if this could help [their business name]?

[Your name]

### Template 2: Free Value First

Subject: I made this for [their business name]

Hi [First Name],

I took the liberty of putting together a [free audit/analysis/report] for [their business name]. [Brief description of what you analyzed — e.g., 'I ran your website through our accessibility checker and found 12 WCAG violations that could expose you to ADA lawsuits.']

Happy to send the full report over — no strings attached. Just thought it might be helpful.

[Your name]
[Title] | [Company]

### Template 3: Referral / Social Proof

Subject: [Mutual connection] suggested I reach out

Hi [First Name],

[Mutual connection] mentioned you might be dealing with [pain point]. We've been working with [vertical] businesses like [named client] to [outcome].

[One specific result: 'They reduced no-shows by 35% in the first month.']

Would you be open to a quick chat about whether we could do something similar for [their business]?

[Your name]

────────────────────────────────────────────────────────────────────────────────

## E3. White-Label Partnership Pitch

Template for approaching US agencies/consultants who could resell your services.

Subject: Delivery partner for your [vertical] clients?

Hi [Name],

I run a [service] team specializing in [vertical]. We work as a white-label delivery partner for US-based [agency type / consultants] who need reliable backend support for their clients.

Here's what we handle:
• [Service 1] — we deliver [output] within [turnaround]
• [Service 2] — we deliver [output] within [turnaround]
• [Service 3] — we deliver [output] within [turnaround]

Your clients get the work done. You keep the relationship and the margin. We stay invisible.

We currently work with [X] agencies and maintain a [X]% client retention rate. Happy to do a trial project for one of your clients at no cost so you can evaluate our quality.

Worth a 15-min call?

[Your name]

────────────────────────────────────────────────────────────────────────────────

## E4. Pricing Guidelines

| Principle | Do | Don't |
| --- | --- | --- |
| Anchor high | Show a premium tier first ($2,000/mo) so Growth tier ($800/mo) feels reasonable | Lead with your cheapest option — it anchors low |
| Show ROI | 'Our route optimization saves 3 hrs/day × $40/hr tech = $2,400/mo value. You pay $400.' | Just list features without connecting to revenue/savings |
| Offer pilot | 'Try us for 30 days at 50% off. If you don't see results, full refund.' | Demand 12-month contracts from new clients with no trust built |
| Bundle services | 'Scheduling + Compliance + Communication = $800/mo (vs $1,200 separately)' | Price each service separately and let client pick — they'll pick only the cheapest |
| Name the competitor | '[Competitor] charges $3,000/mo for this. We deliver the same at $1,200.' | Never mention competitors — clients will comparison shop without context |
| Use 'investment' | 'Your monthly investment is $800' not 'it costs $800' | Use the word 'cost' or 'expense' — frame as investment with returns |

# PART F: OPERATIONS SETUP

## F1. Recommended Team Structure (Starting Lean)

| Role | Count | Responsibilities | Key Skill | India Market Rate |
| --- | --- | --- | --- | --- |
| Delivery Lead / Vertical SME | 1 | Owns service quality, client escalation, SOPs, team training | Domain expertise in chosen vertical + project management | ₹60K-1.2L/mo |
| Automation / Tech Engineer | 1 | Builds workflows, integrations, manages tools, monitors systems | Zapier/Make + Python + API integrations + GoHighLevel | ₹50K-90K/mo |
| Delivery Specialist(s) | 2-3 | Day-to-day service delivery, client communication, reporting | English fluency + attention to detail + vertical knowledge | ₹25K-45K/mo each |
| Sales / BD (India-based) | 1 | Outbound prospecting, partnership outreach, pipeline management | English fluency + LinkedIn/email outreach + CRM management | ₹35K-60K/mo + commission |
| QA / Client Success | 1 (shared) | Quality audits, client satisfaction surveys, issue resolution | Analytical mindset + client empathy + process improvement | ₹30K-50K/mo |

💰 Starting budget: ₹3-5 Lakhs/month (~$3,600-$6,000/month) for a 6-person team delivering to 5-15 clients. Break-even at ~$4,000/month in client revenue with 60%+ gross margins.

## F2. Internal Tool Stack

| Function | Recommended Tool | Cost | Why This Tool |
| --- | --- | --- | --- |
| Project Management | ClickUp or Notion | Free-$10/user/mo | Flexible, handles SOPs + tasks + docs in one place |
| Communication (Internal) | Slack or Microsoft Teams | Free-$8/user/mo | Channel-based comms, integrations with everything |
| CRM (for our sales) | HubSpot Free or GoHighLevel | Free-$97/mo | Track prospects, pipeline, partnerships |
| Client Communication | Slack Connect or email | Free (included) | Real-time client comms without giving them your PM tool |
| Automation | Make.com + Zapier | $29+$20/mo | Make.com for complex workflows, Zapier for simple ones |
| AI / LLM | ChatGPT Plus + Claude Pro | $20+$20/mo | Content generation, data analysis, document drafting |
| Time Tracking | Toggl or Clockify | Free-$10/user/mo | Track delivery hours per client for margin analysis |
| File Storage | Google Workspace | $7/user/mo | Shared drives, docs, sheets — client deliverables |
| Video Calls | Google Meet or Zoom | Free-$15/mo | Client calls, team standups, screen sharing |
| Invoicing | Stripe + Wave or Zoho Invoice | Free-$15/mo | Professional invoicing, recurring billing, payments |

# PART G: KPIs & TRACKING DASHBOARD

What to measure from Day 1. Build this dashboard in Google Sheets or Airtable.

## G1. North Star Metrics

| Metric | Formula | Target (90 Days) | Why It Matters |
| --- | --- | --- | --- |
| Monthly Recurring Revenue (MRR) | Sum of all active monthly contracts | $5,000-$10,000 | Revenue stability — this is your business value |
| Active Clients | # of clients paying monthly | 5-15 | Proof of product-market fit |
| Gross Margin | (Revenue − Delivery Cost) / Revenue | ≥ 60% | Sustainability — below 50% means you're underpricing or overdelivering |
| Client Retention Rate | Clients retained / Total clients (monthly) | ≥ 90%/month | Retention > acquisition. Losing clients = leaking revenue. |

## G2. Sales Metrics

| Metric | Formula | Target | Frequency |
| --- | --- | --- | --- |
| Outreach Volume | # of cold emails/DMs/.calls sent | 100+/week | Weekly |
| Response Rate | Replies / Outreach sent | ≥ 5% | Weekly |
| Meeting Booked Rate | Meetings / Replies | ≥ 30% | Weekly |
| Close Rate | Closed deals / Meetings held | ≥ 20% | Monthly |
| Customer Acquisition Cost (CAC) | Total sales cost / New clients | < $500 | Monthly |
| Pipeline Value | Sum of all active deal values | 3× monthly revenue target | Weekly |

## G3. Delivery Metrics

| Metric | Formula | Target | Frequency |
| --- | --- | --- | --- |
| On-Time Delivery Rate | Deliverables on time / Total deliverables | ≥ 95% | Weekly |
| Error / Rework Rate | Reworks / Total deliverables | ≤ 5% | Weekly |
| Hours per Client per Month | Total delivery hours / Active clients | Track trend | Monthly |
| Automation Rate | Automated tasks / Total tasks | ≥ 60% (and growing) | Monthly |
| NPS (Client Satisfaction) | Survey score (0-10) | ≥ 8 | Monthly (after 30 days) |
| Revenue per Team Member | MRR / Team size | ≥ $1,000 | Monthly |

## G4. Weekly Reporting Template

Every Monday, the Ops Lead fills this out and shares with the team:

| Category | This Week | Last Week | Trend | Notes |
| --- | --- | --- | --- | --- |
| MRR | $___ | $___ | ↑↓→ |  |
| Active Clients | ___ | ___ | ↑↓→ |  |
| New Leads in Pipeline | ___ | ___ | ↑↓→ |  |
| Meetings Booked | ___ | ___ | ↑↓→ |  |
| Proposals Sent | ___ | ___ | ↑↓→ |  |
| Deals Closed | ___ | ___ | ↑↓→ |  |
| On-Time Delivery % | ___% | ___% | ↑↓→ |  |
| Client Issues Open | ___ | ___ | ↑↓→ |  |
| Team Utilization % | ___% | ___% | ↑↓→ |  |
| Biggest Win |  |  |  |  |
| Biggest Challenge |  |  |  |  |
| Next Week Priority |  |  |  |  |

# PART H: 12-WEEK SPRINT CALENDAR

Full quarter at a glance. Print this and pin it on the wall.

| Week | Theme | Key Milestones | Decision Gates |
| --- | --- | --- | --- |
| 1 | 📚 Study & Decide | • Complete Part A study guide • Fill all Part B worksheets • Select vertical(s) + services • Positioning defined | ☐ Vertical selected? ☐ Services selected? ☐ Packages priced? ☐ Team plan approved? |
| 2 | 🔧 Build | • Tools provisioned • Service #1 & #2 workflows built • SOPs written • Sales materials created • 10 pilot prospects contacted | ☐ Workflows tested? ☐ SOPs reviewed? ☐ Sales kit ready? |
| 3 | 🧪 Pilot | • 3-5 pilot clients signed • Onboarding completed • Service #1 delivery begins • Daily standups started • Issues logged | ☐ Pilots onboarded? ☐ Delivery started? ☐ Feedback loop active? |
| 4 | 🧪 Pilot + Refine | • Service #2 delivery begins • Metrics collected • Testimonials drafted • SOPs updated (v2) • Pilot → Paid conversion plan | ☐ Results measured? ☐ SOPs improved? ☐ Conversion offers sent? |
| 5 | 🚀 Launch | • Case studies published • Outbound campaign begins (50 prospects) • Partnership outreach (5 agencies) • Content plan started | ☐ Case studies live? ☐ Outbound running? ☐ Partnership proposals sent? |
| 6 | 🚀 Launch + Build | • Continue outbound (50 more) • Services #3-5 built • 1 industry event attended • Pipeline: 20+ active prospects | ☐ All services ready? ☐ Pipeline healthy? ☐ First non-pilot lead? |
| 7 | 📈 Scale | • First 5-10 paying clients closed • New client onboarding • Delivery team at capacity? • KPI report #1 | ☐ Paying clients signed? ☐ Delivery quality maintained? ☐ Need more hires? |
| 8 | 📈 Scale + Optimize | • Continue closing • Automate more tasks (reduce delivery hours) • Referral program launched • Retrospective meeting | ☐ 10 clients hit? ☐ Margins ≥ 60%? ☐ NPS ≥ 8? |
| 9 | 🔁 Optimize | • Upsell existing clients to Growth/Enterprise • Expand to secondary vertical • Hire if needed • SOPs v3 | ☐ Upsell revenue? ☐ 2nd vertical started? ☐ Team scaled right? |
| 10 | 🔁 Optimize | • Continue outbound at higher volume • Partnership(s) activated • Content marketing accelerating • KPI report #3 | ☐ Partnerships generating? ☐ Content traffic growing? ☐ MRR target on track? |
| 11 | 📊 Review | • Full quarter metrics review • Client interviews (top 3 + bottom 3) • Competitive landscape update • Phase 2 planning begins | ☐ All KPIs reviewed? ☐ Client feedback collected? ☐ Phase 2 direction clear? |
| 12 | 🗺️ Plan Phase 2 | • Phase 2 brief written • Next vertical selected • New services identified • Team growth plan • Budget for next quarter | ☐ Phase 2 approved? ☐ Budget allocated? ☐ Hires planned? |

🚦 Decision Gate: At the end of each week, the team reviews the decision gates. If a gate isn't cleared, STOP and fix it before moving forward. Don't accumulate unresolved issues.

# Quick Reference: Key Numbers

| Metric | Value |
| --- | --- |
| Total services analyzed | 161 |
| Total verticals covered | 34 |
| Platinum services (launch now) | 63 (39.1%) |
| Gold services (high priority) | 46 (28.6%) |
| Sweet spot (High Auto + Low Comp) | 63 services |
| Services ≥75% automatable | 80 (49.7%) |
| Low competition opportunities | 40 (24.8%) |
| Top vertical: HVAC/Plumbing/Electrical | 7 services, 6 Platinum |
| Top vertical: Pool Maintenance | 2 services, 2 Platinum |
| Top vertical: Pet Grooming | 5 services, 3 Platinum |
| Starting team size | 5-6 people |
| Starting monthly budget | ₹3-5 Lakhs ($3,600-$6,000) |
| Break-even target | $4,000/month revenue |
| 90-day MRR target | $5,000-$10,000 |
| 90-day client target | 5-15 active clients |
| Target gross margin | ≥ 60% |
| Target client retention | ≥ 90% monthly |

— End of Implementation Handbook —

Companion files: Handover Document (.docx) + Analysis Spreadsheet (.xlsx)
Use the study guide (Part A) first. Then fill the worksheets (Part B). Then execute (Part C-H).